## Simple Business Risk Register
SIMPLE BUSINESS RISK REGISTER TEMPLATE
RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION NOTES | OWNER | KEY
Give a brief summary of the risk. | What will happen if the risk is not mitigated or eliminated? | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address highest first. | What can be done to lower or eliminate the impact or probability? | Who's responsible? | LEVEL
1-1 Meetings | The project is delayed | 1 | 5 | 5 | Hold 1-1 meetings during breaks | Those with the meetings | 1
15th April Hospital Appointment | The project is delayed - one less person for a few hours possibly | 2 | 5 | 10 | Take out the hospital | Leila | 2
Routing algorithm - high complexity | The project is delayed until MVP functionality is possible | 5 | 3 | 15 | Don't get overambitious with level of complexity | Gabriel, Zarrin | 3
Planning taking longer than expected | Sign-off happens later making progress within project slower | 4 | 2 | 8 | Scheduling each stage and tracking on trello | Everyone | 4
18th April Dentist Appointment | Presentation prep might be delayed | 2 | 5 | 10 | Knock the tooth out the mouth | Kajanan | 5
Running out of free requests on the external API | We will no longer be able to do the routing feature (or we will become broke immediately) | 5 | 2 | 10 | Intentional use of API by running only when everyone is happy
Trainers out for strategy meeting | Delays planning sign off | 3 | 5 | 15 | Continue to research on API and do tasks that aren't affected by this, in the mean time | Everyone

## Scale
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
I M P A C T

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.